## 1A Program Definition
ID | Title | Schedule List ID | Program Name | Program Acronym | Program ID | Program Status | Office Symbol | Program Manager | Program Categorization | Program FY Start | Program FY End | Program Description | Program Stakeholders | Program Technical Objectives | Program Deliverables | Program Warfighter Benefits | Program Approach | Program Image | Latest CCAR Data | Cost Breach Criteria | Schedule Breach Criteria | Technical Performance Breach Criteria | Program Goals | AFRL Investment Justification | Completion Criteria | Program Customers | Comments | Is This Example Data? | Program Type | Phase | Portfolio Type | Program Start Date | Program Completion Date | Is export statement warning needed? | Export Warning Justification | PM External to AFRL | Are other AFRL Msn Orgs participating on this program? | Other AFRL MSN Orgs | CONTACT (NAME/EMAIL/PHONE#/COMPANY) | CONTACT External to AFRL | Program Classification | Distribution Reasons | Date of Determination | Releasing Authority | Distribution Codes | Proposed Primary MAJCOM | Proposed Other MAJCOMs | Proposed Primary DAF Mission Area | Proposed Other DAF Mission Areas | 2023 RW Priority | Arctic Operations Percentage | Climate Change Percentage | Human Capital Percentage | RW Domain | AFRL Space Thrust Area | 2024 RW Priority | Digital Transformation Initiative | Domain | Modified By | Modified | GUID
5 | Operation Viper Storm 49 | 2 | Operation Viper Storm 49 | OSV4 | RW-7O9 | Active | RWID | Morgan Jones | R&D Support | 2023 | 2028 | The Operation Viper Storm 49 is designed to enhance military capabilities through advanced technology and strategic operations. | AFRL AFLCMC | Develop and integrate new technologies, improve operational efficiency, and enhance mission success rates for Operation Viper Storm 49. | Prototype of new technology Comprehensive training programs Detailed operational manuals for Operation Viper Storm 49. | Increased operational readiness, improved mission success rates, and enhanced safety for warfighters involved in Operation Viper Storm 49. | Utilize a phased development approach, incorporating feedback and testing at each stage to ensure the effectiveness of Operation Viper Storm 49. |  |  | 15% overrun | 6+ month schedule slip for deliverable | Can not achieve threshold value | Achieve operational deployment within 3 years, ensure seamless integration with existing systems, and demonstrate significant improvements in mission outcomes. | The investment in Operation Viper Storm 49 is justified by the potential for significant enhancements in military capabilities and operational effectiveness. | Successful deployment of Operation Viper Storm 49, meeting all specified technical objectives and delivering the outlined benefits to warfighters. | Primary: AFRL/RW Secondary: AFLCMC/EB |  | TRUE | R&D-3 (All other Research Programs) | Budgeting | S&T - PBES 6.1/6.2/6.3 S&T Msn Org funded programs - Burdening | 2024-01-02 | 2031-01-30 | TRUE | Data is Export Controlled | FALSE | FALSE |  |  | FALSE | Controlled Unclassified Information | CL- Critical Technology (Export Controlled) | 2024-01-09 | ARFL/RW | D-DoD and DoD Contractors Only | Air Force Materiel Command | ["Air Force Special Operations Command"] | Air Superiority | ["Command and Control","Cyberspace Superiority","Special Operations","Global Integrated ISR","Global Precision Attack","Education and Training"] | digital_material_management | 0 | 0 | 15 | None | None | Operation Viper viability | 85 | air_domain | Morgan Jones

## Personnel
ID | PROGRAM | Title | PERSONNEL | FY | PLANNED | ACTUAL | Modified | Modified By | Created By | GUID
37 | Operation Viper Storm 49 | Morgan Jones | Morgan Jones | 2024 | 0.8 | 0.8 | 2024-01-24 15:04 | Morgan Jones | Timothy C
38 | Operation Viper Storm 50 | Morgan Jones | Morgan Jones | 2025 | 0.8 | 0.8 | 2024-01-24 15:04 | Morgan Jones | Timothy C
39 | Operation Viper Storm 51 | Morgan Jones | Morgan Jones | 2026 | 0.8 | 0.8 | 2024-01-24 15:04 | Morgan Jones | Timothy C
40 | Operation Viper Storm 52 | Morgan Jones | Morgan Jones | 2027 | 1 | 1 | 2024-01-24 15:04 | Morgan Jones | Timothy C
41 | Operation Viper Storm 53 | Morgan Jones | Morgan Jones | 2028 | 1 | 1 | 2024-01-24 15:05 | Morgan Jones | Timothy C
42 | Operation Viper Storm 54 | Morgan Jones | Morgan Jones | 2024 | 0.9 | 0.9 | 2024-01-24 15:05 | Morgan Jones | Timothy C
43 | Operation Viper Storm 55 | Morgan Jones | Morgan Jones | 2025 | 1 | 1 | 2024-01-24 15:05 | Morgan Jones | Timothy C
44 | Operation Viper Storm 56 | Morgan Jones | Morgan Jones | 2026 | 1 | 1 | 2024-01-24 15:08 | Morgan Jones | Timothy C
45 | Operation Viper Storm 57 | Morgan Jones | Morgan Jones | 2027 | 1 | 1 | 2024-01-24 15:05 | Morgan Jones | Timothy C
46 | Operation Viper Storm 58 | Morgan Jones | Morgan Jones | 2028 | 1 | 1 | 2024-01-24 15:06 | Morgan Jones | Timothy C
53 | Operation Viper Storm 59 | Tadej P | Tadej P | 2024 | 0.7 | 0.7 | 2024-01-24 15:07 | Morgan Jones | Timothy C
54 | Operation Viper Storm 60 | Tadej P | Tadej P | 2025 | 0.7 | 0.7 | 2024-01-24 15:08 | Morgan Jones | Timothy C
55 | Operation Viper Storm 61 | Tadej P | Tadej P | 2026 | 0.7 | 0.7 | 2024-01-24 15:08 | Morgan Jones | Timothy C
56 | Operation Viper Storm 62 | Tadej P | Tadej P | 2027 | 1 | 1 | 2024-01-24 15:09 | Morgan Jones | Timothy C
57 | Operation Viper Storm 63 | Tadej P | Tadej P | 2028 | 1 | 1 | 2024-01-24 15:09 | Morgan Jones | Timothy C
58 | Operation Viper Storm 64 | Remco E | Remco E | 2024 | 0.8 | 0.8 | 2024-01-24 15:09 | Morgan Jones | Timothy C
59 | Operation Viper Storm 65 | Remco E | Remco E | 2025 | 0.8 | 0.8 | 2024-01-24 15:10 | Morgan Jones | Timothy C
60 | Operation Viper Storm 66 | Remco E | Remco E | 2026 | 0.9 | 0.9 | 2024-01-24 15:10 | Morgan Jones | Timothy C
61 | Operation Viper Storm 67 | Remco E | Remco E | 2027 | 1 | 1 | 2024-01-24 15:10 | Morgan Jones | Timothy C
62 | Operation Viper Storm 68 | Remco E | Remco E | 2028 | 1 | 1 | 2024-01-24 15:10 | Morgan Jones | Timothy C
63 | Operation Viper Storm 69 | Remco E | Remco E | 2024 | 1 |  | 2023-12-08 15:19 | Morgan Jones | Timothy C
64 | Operation Viper Storm 70 | Jonas V | Jonas V | 2025 | 1 | 1 | 2024-01-24 15:11 | Morgan Jones | Timothy C
65 | Operation Viper Storm 71 | Jonas V | Jonas V | 2026 | 1 | 1 | 2024-01-24 15:11 | Morgan Jones | Timothy C
66 | Operation Viper Storm 72 | Jonas V | Jonas V | 2027 | 1 | 1 | 2024-01-24 15:11 | Morgan Jones | Timothy C
67 | Operation Viper Storm 73 | Jonas V | Jonas V | 2028 | 1 | 1 | 2024-01-24 15:11 | Morgan Jones | Timothy C
302 | Operation Viper Storm 74 | Jonas V | Jonas V | 2024 | 1 | 1 | 2023-12-27 11:01 | Morgan Jones | Timothy C
303 | Operation Viper Storm 75 | Jonas V | Jonas V | 2025 | 1 | 1 | 2024-01-24 15:11 | Morgan Jones | Timothy C
304 | Operation Viper Storm 76 | Jonas V | Jonas V | 2026 | 1 | 1 | 2023-12-27 11:06 | Morgan Jones | Timothy C
305 | Operation Viper Storm 77 | Jonas V | Jonas V | 2027 | 1 | 1 | 2023-12-27 11:06 | Morgan Jones | Timothy C
306 | Operation Viper Storm 78 | Jonas V | Jonas V | 2028 | 1 | 1 | 2023-12-27 11:07 | Morgan Jones | Timothy C

## Facilities
PROGRAM | Title | FACILITY | FY | PLANNED | ACTUAL | GUID
Operation Viper Storm 49 | RW - Classified Lab (Room 777) (%23 Days)-Operation Viper Storm-2024 | RW - Classified Lab (Room 777) (%23 Days)-2024 | 2024 | 260 | 260
Operation Viper Storm 50 | RW - Classified Lab (Room 777) (%23 Days)-Operation Viper Storm-2025 | RW - Classified Lab (Room 777) (%23 Days)-2025 | 2025 | 260 | 260
Operation Viper Storm 51 | RW - Classified Lab (Room 777) (%23 Days)-Operation Viper Storm-2026 | RW - Classified Lab (Room 777) (%23 Days)-2026 | 2026 | 260 | 260
Operation Viper Storm 52 | RW - Classified Lab (Room 777) (%23 Days)-Operation Viper Storm-2027 | RW - Classified Lab (Room 777) (%23 Days)-2027 | 2027 | 260 | 260
Operation Viper Storm 53 | RW - Classified Lab (Room 777) (%23 Days)-Operation Viper Storm-2028 | RW - Classified Lab (Room 777) (%23 Days)-2028 | 2028 | 260 | 260
Operation Viper Storm 54 | RW - Classified Lab (Room 777) (%23 Days)-Operation Viper Storm-2029 | RW - Classified Lab (Room 777) (%23 Days)-2029 | 2029 | 260 | 260

## Schedule
PROGRAM | PROJECT_WBS | WBS | UID | Title | START_DATE | FINISH_DATE | IS_MILESTONE | IS_CRITICAL | START_SLACK | FINISH_SLACK | Created | Created By | Modified | Modified By
Operation Viper | 1.1.8.4.6.1 | 1.1.8.4.6.1 | Kick-off meeting, project team formation, and initial planning. | Initiate Project | 2024-02-10 | 2024-02-16 | TRUE | TRUE |  |  | 2023-05-21 | Vincenzo Nibali | 2023-10-05 | Tadej Pogacar
Operation Viper | 1.2.8.7.6.7 | 1.2.8.7.6.7 | Gather and document detailed requirements from stakeholders. | Define Requirements | 2024-01-27 | 2024-07-27 | FALSE | TRUE |  |  | 2023-07-24 | Vincenzo Nibali | 2024-05-27 | Julian Alaphilippe
Operation Viper | 1.3.1.4.1.6 | 1.3.1.4.1.6 | Design the initial prototype for the alien aircraft detection system. | Design Prototype | 2024-03-13 | 2024-05-14 | TRUE | TRUE |  |  | 2023-06-03 | Nairo Quintana | 2024-12-24 | Egan Bernal
Operation Viper | 1.4.5.5.8.6 | 1.4.5.5.8.6 | Develop the first module of the detection software. | Develop Software Module 1 | 2024-12-03 | 2024-12-05 | TRUE | FALSE |  |  | 2023-04-29 | Egan Bernal | 2023-05-24 | Primoz Roglic
Operation Viper | 1.5.9.1.4.8 | 1.5.9.1.4.8 | Develop the second module of the detection software. | Develop Software Module 2 | 2024-02-25 | 2024-09-21 | FALSE | FALSE |  |  | 2023-10-16 | Chris Froome | 2024-05-30 | Chris Froome
Operation Viper | 1.6.2.1.8.4 | 1.6.2.1.8.4 | Integrate all developed modules into a single system. | Integrate Modules | 2024-04-12 | 2024-09-03 | TRUE | FALSE |  |  | 2023-10-21 | Egan Bernal | 2024-10-25 | Peter Sagan
Operation Viper | 1.7.4.1.5.9 | 1.7.4.1.5.9 | Conduct initial tests on the integrated prototype. | Test Prototype | 2024-06-08 | 2024-07-28 | TRUE | FALSE |  |  | 2023-07-10 | Tadej Pogacar | 2024-04-02 | Egan Bernal
Operation Viper | 1.8.6.5.1.9 | 1.8.6.5.1.9 | Analyze the results of the initial tests and identify issues. | Analyze Test Results | 2024-10-08 | 2024-11-04 | FALSE | FALSE |  |  | 2023-09-03 | Vincenzo Nibali | 2024-11-02 | Vincenzo Nibali
Operation Viper | 1.9.9.6.1.5 | 1.9.9.6.1.5 | Revise the design based on test results and feedback. | Revise Design | 2024-10-20 | 2024-12-07 | FALSE | TRUE |  |  | 2023-09-14 | Primoz Roglic | 2024-01-11 | Julian Alaphilippe
Operation Viper | 1.10.9.3.8.3 | 1.10.9.3.8.3 | Develop the final version of the detection system. | Develop Final Product | 2024-12-05 | 2024-12-06 | FALSE | TRUE |  |  | 2023-05-09 | Primoz Roglic | 2024-01-31 | Vincenzo Nibali
Operation Viper | 1.11.5.3.8.2 | 1.11.5.3.8.2 | Conduct comprehensive testing on the final product. | Conduct Final Testing | 2024-02-21 | 2024-10-28 | TRUE | TRUE |  |  | 2023-10-15 | Nairo Quintana | 2024-03-17 | Chris Froome
Operation Viper | 1.12.9.3.6.9 | 1.12.9.3.6.9 | Prepare all necessary documentation for the system. | Prepare Documentation | 2024-12-01 | 2024-12-19 | TRUE | TRUE |  |  | 2023-10-10 | Mark Cavendish | 2023-11-19 | Egan Bernal
Operation Viper | 1.13.2.9.7.6 | 1.13.2.9.7.6 | Provide training and support to the end-users. | Training & Support | 2024-03-18 | 2024-10-15 | TRUE | FALSE |  |  | 2023-03-13 | Julian Alaphilippe | 2023-04-05 | Julian Alaphilippe
Operation Viper | 1.14.3.4.8.7 | 1.14.3.4.8.7 | Plan the deployment strategy and logistics. | Deployment Planning | 2024-12-30 | 2024-12-31 | FALSE | TRUE |  |  | 2023-01-28 | Mark Cavendish | 2024-04-08 | Nairo Quintana
Operation Viper | 1.15.1.1.1.9 | 1.15.1.1.1.9 | Deploy the initial version of the system in a controlled environment. | Initial Deployment | 2024-12-02 | 2024-12-30 | FALSE | TRUE |  |  | 2023-02-26 | Primoz Roglic | 2024-10-25 | Vincenzo Nibali
Operation Viper | 1.16.3.5.1.8 | 1.16.3.5.1.8 | Monitor the deployment and collect performance data. | Monitor Deployment | 2024-11-03 | 2024-12-20 | TRUE | TRUE |  |  | 2023-06-18 | Mark Cavendish | 2023-10-22 | Peter Sagan
Operation Viper | 1.17.5.4.8.2 | 1.17.5.4.8.2 | Collect feedback from the initial users of the system. | User Feedback Collection | 2024-10-08 | 2024-12-08 | TRUE | TRUE |  |  | 2023-02-15 | Julian Alaphilippe | 2023-04-17 | Primoz Roglic
Operation Viper | 1.18.9.2.8.3 | 1.18.9.2.8.3 | Analyze the feedback and identify areas for improvement. | Analyze Feedback | 2024-02-20 | 2024-11-20 | FALSE | TRUE |  |  | 2023-01-02 | Peter Sagan | 2023-09-28 | Mark Cavendish
Operation Viper | 1.19.2.9.8.2 | 1.19.2.9.8.2 | Make final adjustments based on the feedback analysis. | Final Adjustments | 2024-04-30 | 2024-05-24 | FALSE | FALSE |  |  | 2023-02-02 | Vincenzo Nibali | 2023-08-11 | Peter Sagan
Operation Viper | 1.20.4.7.3.1 | 1.20.4.7.3.1 | Officially close the project and hand over to maintenance. | Project Closure | 2024-03-31 | 2024-07-12 | FALSE | FALSE |  |  | 2023-05-03 | Vincenzo Nibali | 2024-08-26 | Tadej Pogacar

## Budget
PROGRAM | Title | WBS | FY | AMOUNT | CATEGORY | PROJECT | Modified | Modified By | GUID | PROGRAM: GUID | PROJECT: GUID
Operation Storm | Project Alpha |  | 2025 | 500000 | 6.2 | Project Alpha | 2024-01-15 | Alice Johnson
Operation Storm | Project Beta |  | 2026 | 200000 | 6.2 | Project Beta | 2024-04-10 | Bob Lee
Operation Storm | Project Beta |  | 2027 | 700000 | 6.2 | Project Beta | 2024-07-01 | Charlie Brown
Operation Storm | Project Beta |  | 2025 | 300000 | 6.3 | Project Beta | 2024-09-15 | Dana White
Operation Storm | Project Alpha |  | 2026 | 500000 | 6.3 | Project Alpha | 2024-01-15 | Alice Johnson
Operation Storm | Project Alpha |  | 2027 | 200000 | 6.3 | Project Alpha | 2024-04-10 | Bob Lee
Operation Storm | Project Beta |  | 2028 | 700000 | 6.3 | Project Beta | 2024-07-01 | Charlie Brown
Operation Storm | Project Alpha |  | 2028 | 300000 | 6.2 | Project Alpha | 2024-09-15 | Dana White
Operation Storm | Project Beta |  | 2029 | 500000 | 6.3 | Project Beta | 2024-04-10 | Bob Lee
Operation Storm | Project Alpha |  | 2030 | 200000 | 6.3 | Project Alpha | 2024-07-01 | Charlie Brown

## Projects
Program | Name | WBS | Project Start Date | Project End Date | Objectives | Technical Approach | Status | Description | POC | Project Image Filespec | Comments | Modified | Created | Created By | Modified By | GUID | Program: GUID
Operation Storm | Project Alpha | 1.1 | 2024-01-01 | 2024-06-30 | Develop initial detection algorithms for alien aircraft. | Use machine learning techniques to analyze radar data. | In Progress | Project Alpha focuses on the development of foundational algorithms for detecting alien aircraft using advanced radar analysis. | John Smith | alpha_project_image.png | Initial phase underway with promising results. | 2024-01-15 | 2024-01-01 | Alice Johnson | Bob Lee
Operation Storm | Project Beta | 1.2 | 2024-07-01 | 2024-12-31 | Integrate detection algorithms with hardware sensors. | Develop interfaces and protocols for hardware integration. | Planned | Project Beta aims to integrate the detection algorithms developed in Project Alpha with physical hardware sensors to create a complete detection system. | Jane Doe | beta_project_image.png | Project scheduled to start in July 2024. | 2024-06-30 | 2024-06-01 | Charlie Brown | Dana White

## Quantitative
PROGRAM | WBS | Title | NAME | UNITS | THRESHOLD | OBJECTIVE | CURRENT | CURRENT_DATE | VERIFYMETHOD | COMMENTS | POC | MEASURE_BL | UID | Modified | Modified By | ID | GUID | PROGRAM: GUID
Operation Strom | 1.1 Project Alpha | Develop initial detection algorithms for alien aircraft. | Develop initial detection algorithms for alien aircraft. | % | 70 | 50 |  | 2024-01-31 | Test |  | Morgan Jones | FALSE |  | 2024-09-15 | Tadej P | 12
Operation Strom | 1.2.2 Signal Processing Algorithm Development | Develop algorithms for processing radar signals to detect potential alien aircraft. | Develop algorithms for processing radar signals to detect potential alien aircraft. | % | 60 | 90 | 0 | 2024-01-31 | Analysis |  | Morgan Jones | FALSE |  | 2024-01-15 | Tadej P | 264
Operation Strom | 1.2.3 Machine Learning Integration with Radar Data | Integrate the machine learning model with radar data to improve detection accuracy. | Integrate the machine learning model with radar data to improve detection accuracy. | % | 90 | 270 | 0 | 2024-01-31 | Test |  | Morgan Jones | FALSE |  | 2024-04-10 | Tadej P | 265
Operation Strom | 1.2.3.2 Simulated Data Testing of Integrated System | Test the integrated system using simulated radar data to validate performance. | Test the integrated system using simulated radar data to validate performance. | % | 75 | 85 | 0 | 2024-01-31 | Analysis |  | Morgan Jones | TRUE |  | 2024-07-01 | Tadej P | 269

## Quantitative Progress
PROGRAM | TPM | Title | PERFORMANCEDATE | PREDICT | TOLERANCE | ACTUAL | ONTRACK | WHYNOT | GUID
Operation Storm | Signal Processing Algorithm Development |  | 2021-12-01 | 100 |  |  | TRUE
Operation Storm | Machine Learning Integration with Radar Data |  | 2022-11-30 | 60 |  |  | TRUE
Operation Storm | Simulated Data Testing of Integrated System |  | 2024-07-30 | 55 |  |  | TRUE
Operation Storm | Signal Processing Algorithm Development |  | 2024-10-01 | 20 |  | 0 | FALSE
Operation Storm | Machine Learning Integration with Radar Data |  | 2024-02-07 | 0 |  | 0 | TRUE
Operation Storm | Simulated Data Testing of Integrated System |  | 2024-02-07 | 0 |  | 0 | TRUE
Operation Storm | Signal Processing Algorithm Development |  | 2025-01-01 | 60 |  | 40 | FALSE
Operation Storm | Machine Learning Integration with Radar Data |  | 2026-02-02 | 80 |  | 75 | FALSE
Operation Storm | Simulated Data Testing of Integrated System |  | 2024-05-01 | 20 |  | 10 | TRUE
Operation Storm | Signal Processing Algorithm Development |  | 2024-11-01 | 40 |  | 30 | TRUE
Operation Storm | Machine Learning Integration with Radar Data |  | 2024-05-01 | 30 |  | 0 | TRUE
Operation Storm | Simulated Data Testing of Integrated System |  | 2024-11-01 | 60 |  | 30 | TRUE
Operation Storm | Machine Learning Integration with Radar Data |  | 2025-03-01 | 65 |  | 30 | TRUE
Operation Storm | Simulated Data Testing of Integrated System |  | 2025-04-01 | 100 |  | 80 | TRUE

## Products
PROGRAM | PROJECT | WBS | NAME | TYPE | Modified By | DESCRIPTION | IMAGE | RL_INITIAL | RL_FINAL | RLTYPE | ENDSTATE | Created By | Projected Tech Transition Path | Technology Availability Date | Tech Availability Date Status | Primary Transition Path | Transition Status | Applicable Transition Types | Expected Transition Customer | Date of Expected Transition to Customer | Is Transition Funding Available? | Transition Funding Source | Type of Transition Funding | Transition Funding Amount | Potential for Tech Transfer? | Transfer Method Upon Completion | Tech Transfer Comments | GUID | PROGRAM: GUID | PROJECT: GUID
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.3.1 Data Collection for Machine Learning | Data Collection for Machine Learning | Software | Mason Jones | Integrate the machine learning model with radar data to improve detection accuracy. |  | 1 | 4 | SRL |  | Mason Jones | Internal Transition | 2025-12-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2025-12-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.8 System Architecture Design | 1.2.8 System Architecture Design | Software | Mason Jones | Design the overall system architecture for the alien aircraft detection system. |  | 1 | 4 | SRL |  | Mason Jones | Internal Transition | 2025-12-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2025-12-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.6 Hardware Integration Testing | 1.2.6 Hardware Integration Testing | Software | Mason Jones | Test the integration of hardware components with the detection system. |  | 1 | 4 |  |  | Mason Jones | Internal Transition |  | Completed | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2023-12-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.7 User Interface Development | 1.2.7 User Interface Development | Software | Mason Jones | Develop the user interface for the detection system to allow easy operation by military personnel. |  | 1 | 4 | SRL |  | Mason Jones | Internal Transition | 2025-12-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2025-12-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.8 System Architecture Design | 1.2.8 System Architecture Design | Software | Mason Jones | Design the overall system architecture for the alien aircraft detection system. |  | 1 | 5 | SRL |  | Mason Jones | Internal Transition | 2024-01-31 | Completed | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2024-01-31 | FALSE |  |  |  | FALSE
Operation Storm | Integrate Modules | 1.1.4 Field Deployment and Initial Testing | 1.1.4 Field Deployment and Initial Testing | Hardware | Mason Jones | Deploy the detection system in a field setting and conduct initial testing. |  | 2 | 4 | TRL |  | Mason Jones | Internal Transition | 2024-12-31 | On-Schedule | Internal Transition | Need Info | ["Technology product for use in a prototyping effort"] |  | 2024-12-31 | FALSE |  |  |  | FALSE
Operation Storm | Integrate Modules | 1.1.3 Algorithm Development and Simulation | 1.1.3 Algorithm Development and Simulation | Software | Mason Jones | Integrate the developed algorithms with the existing data processing pipeline. |  | 2 | 4 | SRL |  | Mason Jones | Internal Transition | 2024-12-31 | On-Schedule | Internal Transition | Need Info | ["Technology product for use in a prototyping effort"] |  | 2024-12-31 | FALSE |  |  |  | FALSE
Operation Storm | Integrate Modules | 1.1.2 Requirement Analysis and Specification | 1.1.2 Requirement Analysis and Specification | Other | Mason Jones | Analyze the requirements and specify the functional and non-functional requirements for the detection system. |  | 4 | 6 | TRL |  | Mason Jones | Internal Transition | 2025-12-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2025-12-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.8 System Architecture Design | 1.2.8 System Architecture Design | Software | Mason Jones | Design the overall system architecture for the alien aircraft detection system. |  | 1 | 4 | SRL |  | Mason Jones | Internal Transition | 2024-01-31 | Completed | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2024-01-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.2 Signal Processing Algorithm Development | 1.2.2 Signal Processing Algorithm Development | Software | Mason Jones | Develop algorithms for processing radar signals to detect potential alien aircraft. |  | 1 | 5 | SRL |  | Mason Jones | Internal Transition | 2025-03-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2025-03-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.2 Signal Processing Algorithm Development | 1.2.2 Signal Processing Algorithm Development | Software | Mason Jones | Develop algorithms for processing radar signals to detect potential alien aircraft. |  | 1 | 5 | SRL |  | Mason Jones | Internal Transition | 2024-12-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2024-12-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.2 Signal Processing Algorithm Development | 1.2.2 Signal Processing Algorithm Development | Software | Mason Jones | Develop algorithms for processing radar signals to detect potential alien aircraft. |  | 5 | 5 | SRL |  | Mason Jones | Internal Transition | 2024-08-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2024-08-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.2 Signal Processing Algorithm Development | 1.2.2 Signal Processing Algorithm Development | Software | Mason Jones | Develop algorithms for processing radar signals to detect potential alien aircraft. |  | 1 | 5 | SRL |  | Mason Jones | Internal Transition | 2025-01-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2025-01-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.2 Signal Processing Algorithm Development | 1.2.2 Signal Processing Algorithm Development | Software | Mason Jones | Develop algorithms for processing radar signals to detect potential alien aircraft. |  | 1 | 5 | SRL |  | Mason Jones | Internal Transition | 2025-03-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2025-03-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.3.2.3 Field Testing with Real Data | 1.2.3.2.3 Field Testing with Real Data | Software | Mason Jones | Conduct field tests of the detection system using real radar data. |  | 3 | 7 | SRL |  | Mason Jones | Internal Transition | 2025-12-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2025-12-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.3.2.4 Performance Analysis and Optimization | 1.2.3.2.4 Performance Analysis and Optimization | Process | Mason Jones | Analyze the performance of the detection system and optimize it for better accuracy and efficiency. |  | 1 | 5 | SRL |  | Mason Jones | Internal Transition | 2025-03-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2025-03-31 | FALSE |  |  |  | FALSE
Operation Storm | Develop initial detection algorithms for alien aircraft. | 1.2.6 Hardware Integration Testing | 1.2.6 Hardware Integration Testing | Software | Mason Jones | Test the integration of hardware components with the detection system. |  | 1 | 4 | SRL |  | Mason Jones | Internal Transition | 2024-07-31 | On-Schedule | Internal Transition | On-Schedule | ["Technology product for use in a prototyping effort"] |  | 2024-07-31 | FALSE |  |  |  | FALSE

## Product Progression
Title | PROGRAM | Modified By | PRODUCT | PLANNED | ACTUAL | DATE | GUID | PRODUCT: GUID | PROGRAM: GUID
| Operation Storm | Mason Jones | Preprocessed Radar Datasets | 1 |  | 2024-04-29
| Operation Storm | Mason Jones | Preprocessed Radar Datasets | 2 |  | 2024-06-27
| Operation Storm | Mason Jones | Preprocessed Radar Datasets | 3 |  | 2024-08-30
| Operation Storm | Mason Jones | Preprocessed Radar Datasets | 4 |  | 2025-02-28
| Operation Storm | Mason Jones | Preprocessed Radar Datasets | 6 |  | 2025-10-20
| Operation Storm | Mason Jones | Preprocessed Radar Datasets | 1 | 1 | 2024-01-15
| Operation Storm | Mason Jones | Preprocessed Radar Datasets | 2 | 2 | 2024-04-01
| Operation Storm | Mason Jones | Preprocessed Radar Datasets | 3 |  | 2024-09-03
| Operation Storm | Mason Jones | Preprocessed Radar Datasets | 4 |  | 2024-12-16
| Operation Storm | Mason Jones | Data Collection Protocols Document | 1 | 1 | 2023-02-28
| Operation Storm | Mason Jones | Data Collection Protocols Document | 2 | 2 | 2023-04-28
| Operation Storm | Mason Jones | Data Collection Protocols Document | 3 | 3 | 2023-07-05
| Operation Storm | Mason Jones | Data Collection Protocols Document | 4 | 4 | 2023-09-29
| Operation Storm | Mason Jones | Data Collection Protocols Document | 1 | 1 | 2023-09-18
| Operation Storm | Mason Jones | Integration Test Reports | 2 | 2 | 2023-10-06
| Operation Storm | Mason Jones | Integration Test Reports | 3 | 3 | 2023-10-27
| Operation Storm | Mason Jones | Integration Test Reports | 4 | 4 | 2023-11-30
| Operation Storm | Mason Jones | Hardware-Software Interface Specifications | 1 |  | 2024-04-15
| Operation Storm | Mason Jones | Hardware-Software Interface Specifications | 2 |  | 2024-05-13
| Operation Storm | Mason Jones | Hardware-Software Interface Specifications | 3 |  | 2024-09-16
| Operation Storm | Mason Jones | Hardware-Software Interface Specifications | 4 |  | 2025-03-10
| Operation Storm | Mason Jones | User Interface Prototypes | 1 | 1 | 2023-04-27
| Operation Storm | Mason Jones | User Interface Prototypes | 2 | 2 | 2023-08-30
| Operation Storm | Mason Jones | User Interface Prototypes | 3 | 3 | 2023-09-30
| Operation Storm | Mason Jones | User Interface Prototypes | 4 | 4 | 2024-01-15
| Operation Storm | Mason Jones | UI/UX Design Documents | 1 | 1 | 2024-02-28
| Operation Storm | Mason Jones | UI/UX Design Documents | 2 |  | 2024-04-29
| Operation Storm | Mason Jones | UI/UX Design Documents | 3 |  | 2024-06-28
| Operation Storm | Mason Jones | UI/UX Design Documents | 4 |  | 2024-08-30
| Operation Storm | Mason Jones | Field Test Reports | 2 | 2 | 2023-04-28
| Operation Storm | Mason Jones | Field Test Reports | 3 | 3 | 2023-09-01
| Operation Storm | Mason Jones | Field Test Reports | 3 |  | 2024-07-30
| Operation Storm | Mason Jones | Field Test Reports | 4 |  | 2024-11-01
| Operation Storm | Mason Jones | Field Test Reports | 5 |  | 2025-10-31
| Operation Storm | Mason Jones | Test Case Documentation | 2 | 2 | 2024-01-30
| Operation Storm | Mason Jones | Test Case Documentation | 3 |  | 2024-05-01
| Operation Storm | Mason Jones | Test Case Documentation | 3 |  | 2024-07-31
| Operation Storm | Mason Jones | Test Case Documentation | 4 |  | 2024-11-29
| Operation Storm | Mason Jones | Test Case Documentation | 4 |  | 2024-11-29
| Operation Storm | Mason Jones | Optimization Algorithms | 4 | 4 | 2022-10-31
| Operation Storm | Mason Jones | Optimization Algorithms | 4 | 4 | 2023-01-10
| Operation Storm | Mason Jones | Optimization Algorithms | 5 | 5 | 2023-10-16
| Operation Storm | Mason Jones | Optimization Algorithms | 5 | 5 | 2024-02-28
| Operation Storm | Mason Jones | Optimization Algorithms | 6 |  | 2024-07-31
| Operation Storm | Mason Jones | System Design Blueprints | 1 |  | 2024-04-30
| Operation Storm | Mason Jones | System Design Blueprints | 2 |  | 2024-07-01
| Operation Storm | Mason Jones | System Design Blueprints | 3 |  | 2024-09-30
| Operation Storm | Mason Jones | System Design Blueprints | 4 |  | 2025-04-01
| Operation Storm | Mason Jones | System Design Blueprints | 5 |  | 2025-09-30
| Operation Storm | Mason Jones | Design Review Meeting Minutes | 5 | 5 | 2024-02-15
| Operation Storm | Mason Jones | Design Review Meeting Minutes | 6 |  | 2024-06-30
| Operation Storm | Mason Jones | Design Review Meeting Minutes | 1 | 1 | 2023-07-01
| Operation Storm | Mason Jones | Design Review Meeting Minutes | 2 | 2 | 2024-02-29
| Operation Storm | Mason Jones | Design Review Meeting Minutes | 3 |  | 2024-04-30
| Operation Storm | Mason Jones | Design Review Meeting Minutes | 4 |  | 2024-05-15
| Operation Storm | Mason Jones | Design Review Meeting Minutes | 5 |  | 2024-05-31
| Operation Storm | Mason Jones | Detection Algorithms Codebase | 1 | 1 | 2023-11-01
| Operation Storm | Mason Jones | Detection Algorithms Codebase | 2 | 2 | 2023-12-31
| Operation Storm | Mason Jones | Detection Algorithms Codebase | 3 | 3 | 2024-01-30
| Operation Storm | Mason Jones | Detection Algorithms Codebase | 4 | 4 | 2024-02-29
| Operation Storm | Mason Jones | Detection Algorithms Codebase | 5 |  | 2024-06-30
| Operation Storm | Mason Jones | Integrated System Prototype | 1 | 1 | 2023-10-01
| Operation Storm | Mason Jones | Integrated System Prototype | 5 | 5 | 2024-02-29
| Operation Storm | Mason Jones | Integrated System Prototype | 1 | 1 | 2023-11-01
| Operation Storm | Mason Jones | Integrated System Prototype | 2 |  | 2024-05-01
| Operation Storm | Mason Jones | Integrated System Prototype | 3 |  | 2024-06-01
| Operation Storm | Mason Jones | Integrated System Prototype | 4 |  | 2024-07-01
| Operation Storm | Mason Jones | Integrated System Prototype | 5 |  | 2024-09-30
| Operation Storm | Mason Jones | Integration Test Logs | 1 | 1 | 2024-01-17
| Operation Storm | Mason Jones | Integration Test Logs | 2 | 2 | 2024-03-01
| Operation Storm | Mason Jones | Integration Test Logs | 3 | 3 | 2024-04-01
| Operation Storm | Mason Jones | Integration Test Logs | 4 |  | 2024-05-01
| Operation Storm | Mason Jones | Integration Test Logs | 5 |  | 2024-08-01
| Operation Storm | Mason Jones | Deployed System Configuration | 1 | 1 | 2024-01-31
| Operation Storm | Mason Jones | Deployed System Configuration | 3 | 3 | 2024-02-06
| Operation Storm | Mason Jones | Deployed System Configuration | 5 | 5 | 2024-04-06
| Operation Storm | Mason Jones | Deployed System Configuration | 6 |  | 2024-05-06
| Operation Storm | Mason Jones | Initial Test Results | 2 | 2 | 2024-04-06
| Operation Storm | Mason Jones | Initial Test Results | 4 |  | 2024-07-15
| Operation Storm | Mason Jones | Initial Test Results | 5 |  | 2024-10-01
| Operation Storm | Mason Jones | Final Evaluation Summary | 2 | 2 | 2024-03-15
| Operation Storm | Mason Jones | Final Evaluation Summary | 4 |  | 2024-06-02
| Operation Storm | Mason Jones | Final Evaluation Summary | 5 |  | 2024-07-20
| Operation Storm | Mason Jones | Final Evaluation Summary | 6 |  | 2024-10-01

## Risks
PROGRAM | WBS | Title | NAME | TYPE | STATUS | STATEMENT | HANDLINGSTRATEGY | MITIGATION | OPENDATE | STATUSDATE | TARGETDATE | CLOSE_DATE | INITIALC | INITIALL | CURRENTC | CURRENTL | TARGETC | TARGETL | RATIONALEL | RATIONALEC | AFFECTEDMETRIC | COMMENTS | OWNER | GUID | PROGRAM: GUID
Operation Storm | System Architecture Design (1.2.8) | Inadequate system design leading to integration challenges. | Inadequate system design leading to integration challenges. | ["Cost"] | Open |  | Accept | Conduct thorough design reviews and stakeholder meetings. | 2023-08-17 | 2023-08-17 | 2024-05-01 |  | 4 | 1 | 4 | 1 | 1 | 1 |  |  |  |  | Tadej P
Operation Storm | Hardware Integration Testing (1.2.6) | Hardware compatibility issues with existing systems. | Hardware compatibility issues with existing systems. | ["Cost","Schedule"] | Open |  | Accept | Perform early and frequent hardware-software integration tests. | 2024-01-24 | 2024-01-24 |  |  | 2 | 3 | 2 | 3 | 1 | 1 |  |  |  |  | Tadej P
Operation Storm | User Interface Development (1.2.7) | User interface not meeting end-user requirements. | User interface not meeting end-user requirements. | ["Cost","Schedule"] | Open |  | Accept | Engage end-users in the design process and conduct usability testing. | 2024-01-24 | 2024-01-24 |  |  | 2 | 4 | 1 | 4 | 1 | 1 |  |  |  |  | Tadej P
Operation Storm | Field Testing with Real Data (1.2.3.2.3) | Field conditions affecting the reliability of test results. | Field conditions affecting the reliability of test results. | ["Schedule"] | Open |  | Mitigate | Plan for multiple field tests in varying conditions. | 2024-01-24 | 2024-01-24 |  |  | 4 | 2 | 4 | 1 | 1 | 1 |  |  |  |  | Tadej P
Operation Storm | Performance Analysis and Optimization (1.2.3.2.4) | Optimization efforts not yielding significant performance improvements. | Optimization efforts not yielding significant performance improvements. | ["Performance"] |  |  | Monitor | Continuously monitor performance and adapt optimization strategies. | 2024-01-25 | 2024-01-31 | 2024-03-31 |  | 4 | 2 | 1 | 1 | 1 | 1 |  |  |  |  | Tadej P
Operation Storm | Requirement Analysis and Specification (1.1.2.1) | Misinterpretation of stakeholder requirements. | Misinterpretation of stakeholder requirements. | ["Performance"] |  |  | Accept | Hold regular requirement validation sessions with stakeholders. | 2024-01-25 | 2024-01-25 | 2024-03-31 |  | 3 | 2 | 1 | 1 | 1 | 1 |  |  |  |  | Tadej P

## Risk Burndown
Title | RISK | MITIGATION_PLAN | COMPLETION_DATE | NEWC | NEWL | PROGRAM | GUID
| Inadequate system design leading to integration challenges. | Conduct thorough design reviews and stakeholder meetings. | 2024-03-04 | 3 | 3 | Operation Storm
| Hardware compatibility issues with existing systems. | Perform early and frequent hardware-software integration tests. | 2024-06-03 | 1 | 1 | Operation Storm
| User interface not meeting end-user requirements. | Engage end-users in the design process and conduct usability testing. | 2024-07-15 | 4 | 3 | Operation Storm
| Field conditions affecting the reliability of test results. | Plan for multiple field tests in varying conditions. | 2024-08-19 | 2 | 1 | Operation Storm
| Optimization efforts not yielding significant performance improvements. | Continuously monitor performance and adapt optimization strategies. | 2024-02-15 | 1 | 1 | Operation Storm
| Misinterpretation of stakeholder requirements. | Hold regular requirement validation sessions with stakeholders. | 2024-02-28 | 1 | 1 | Operation Storm

## CTC & COI
Program | CTCCOI | Primary | Sub | ProgramLookUp
Operation Storm | CTC | Software Simulation | Modeling and Simulation | Operation Storm
Operation Storm | COI | Advanced Radar | Integrated Radar Demonstrators | Operation Storm